## SLOC
Team Number: | 3
Week: | 11
Program Size (SLOC) | Actual | Notes
Base
Added | 1519
Deleted | 915
Modified | 93
Reused | 3120 | backend, frontend, teamsite
From COTS | 2502
Total New SLOC | 8149

## COTS
List of third-party components being considered for use in the system as of 11/28/2018
Component name | Functions of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black box | White box | Modify code
Flask | Python web framework | N/A | Backend server | Y
JSON web token | Authentication service standard | N/A | Backend server | Y
React | Javascript library | N/A | Frontend system |  | Y
Webpack | Javascript module bundler | N/A | Frontend system | Y
AWS | Cloud web service used for production | N/A | Backend system | Y
Heroku | Cloud web service used for prototyping | N/A | Backend system | Y
Swagger UI | API documentation and testing | N/A | Backend documentation |  |  | Y
Node JS | JS runtime environment | N/A | Frontend building environment | Y
Creative TIM | Component library | N/A | Style web app |  |  | Y
Material | CSS framework | N/A | Style web app | Y
mLab | database hosting service | N/A | Backend system | Y
MongoDB | Database | N/A | Store content ideas / user account info / team performance info etc | Y
Components that were filtered in the previous week
Component name | Rationale for filtering the component |  | Notes and References
none

## Progress
Progress Description
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. List your top priority works that must be accomplished in this week
1 | Finish updating DC package documentations for As built package
2 | Implement user manual and technical manual
3 | Finalize swagger API documentation in codebase
4 | Modify frontend based on TRR feedback
5 | Deploy webapp on AWS
6 | Fix integrating frontend and backend
7 | Refactor config file for production
8 | Modify content admin pages
9 | Implement exporting publishing calendar to CSV file
10 | Implement automated tests (auth, users, ideas, goals endpoints) / End to end testing for main user workflow
11 | Implement Transition Plan / Support Plan documentation
12 | Update team site (fix the final deliverable page), update project description, team roles
13
14
15
B. List dependencies or things/decision that you waiting for in this week
1 | Waiting for more TRR feedback
2
C. List your accomplishments from the previous week
1 | Made improvements to idea endpoints on the backend API
2 | Improved frontend UI for idea management system
3 | Prepare for TRR presentation
4 | Updated DC package documents based on client feedback for final delivery
5 | Clean up backend API endpoints
6 | Updated Diagrams
7 | More implementation increments on frontend user, goals, and verticals
8 | Redone dashboards and goal boards frontend and backend
9 | Refactor user model to account for new user role types
10 | Refactor auth decorators to account for new user role types
11 | Create goal model
12 | Create GET/POST routes for goal list
13 | Create GET/POST/PUT/DELETE routes for goals route