## Risk
Top Project Risks as 11/28/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed | No. of Weeks Active
This Week | Last Week
1 | 1 | The product developed may not meet client's needs | short on time, core capability are not met or unfinished product, poor communication with the client | Implement must-have functionalities, finish implementing documentation | 8 | 6 | 48 | Long turnaround time from the client. The scope has been narrowed down but changed again after the client meeting. Considering the point of time we stand in the semester, we may have insufficient time for development. CCD is postponed to the following week. | 11
2 | 4 | Concurrency Issue | Multiple users edit at the same time | Handle each request one at a time | 4 | 4 | 16 | Proposed fallback MVP by negotiating with the client about implementation decisions: limiting user priviledge on editing pitches | 4
3 | 2 | Potential high learning curve for maintainers | Majority of the team do not plan to take CS577B. Need to have smooth handoff | Provide documentation to ensure smooth knowledge transfer | 3 | 4 | 12 | Decided to use React for frontend development and later found out that maintainers do not have React experience | 9

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Class assignment and thanksgiving holiday shortened development time | Plan better in the future
2
3
4
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Class assignment was difficult and took longer time to complete than expected | Put in extra effort to ensure tasks can be completed by the As-built pacakage delivery deadline
2 | Client proposed to change UI right before the TRR | Put extra effort and made it happen, work with the client to scope the project
3
4
5
6
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Delayed feedback from the client side developer on tech used in the system | Ping the client representative again and wait for the client side developer feedback
2
3
4
5