## SLOC
Team Number: | 3
Week: | 1 | 9/5-9/24 win-win session was delayed so deadline for our team on this report was pushed back to 9/24
Program Size (SLOC) | Actual | Notes
Base
Added | 331
Deleted | -120
Modified | 0 | Modified 15 files
Reused | 0
From COTS | 1 | CSS Lib: BULMA framework
Total New SLOC | 212

## COTS
List of third-party components being considered for use in the system as of 09/23/2018
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
BULMA | CSS framework | TBD | TBD | Y
Scrapy | Python web crawler framework | TBD | TBD | Y
Crawler4J | Java web crawler framework | TBD | TBD | Y
Django | Python web framework | TBD | TBD | Y
Apache Solr-lucene | Search engine framwork | TBD | TBD | Y
Elasticsearch | Search engine framwork | TBD | TBD | Y
MySQL / PostgreSQL /MongoDB | Database | TBD | TBD | Y
Spring Boot | Java web framework | TBD | TBD | Y
Apache Nutch | Production Java web crawler | TBD | TBD | Y
Twitter API | Data source access | TBD | TBD | Y
Facebook API | Data source access | TBD | TBD | Y
Flask | Python web framework | TBD | TBD | Y
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Implement and polish UI prototype
2 | Investigate API based trend identifier system, as a first step, investigate if Facebook API can track user activity on public post (endpoints). Then investigate if Facebook API can help identify trend.
3 | MVP utilizing Facebook API to pull some info from Facebook to prove if the concept is feasible
4 | Competitive analysis (feature matrix, go over all existing products, identify the must-haves, identify things to differentiate ours from other compatitors, what we can do better? What more we can offer?)
5 | Identify two personas of potential users
6 | Work with client to better scope the project (core requirements)
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Client's feedback on current work flow (content creator workflow, snapshot of their spreadsheet)
2 | Client's feedback on pain points (conduct interview with content creators to identify it)
3
4
5
C. | List your accomplishments from the previous week
1 | Conducted Win-win negotiation #1 with the client on 9/18
2 | Conducted Win-win negotiation #2 with the client on 9/21
3 | Started preliminary competitive research (Facebook API, Twitter API, competitor sites, data scraping options)
4 | Started prototyping (UI & UX)
5 | Started architecture planning & design
6 | Conducted risk analysis
7 | Identified prototype tasks
8 | Improved the team website
9 | Completed group assignments (PC-2)