## Risk
Top Project Risks as of 09/23/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | N/A | Trend identification, are we able to idenfity trending content (rank the topics by frequency?) | Vague definition of trend from the client, Computational complexity of trend identification: underlying algorithm design / architecure design(How to bin trends by topics) | Figure out current workflow in system 1 on identifying trends (including interviewing the content creators) | 5 | 10 | 50 | N/A | 1
2 | N/A | The product developed may not meet client's needs | Potentially unbounded scope, vague project description, no direct access to endusers (content creators) | More discussion with the client, conduct usability testing to gain enduser feedback on product design (use Validately.com to conduct a survey or at least use google survey) | 4 | 10 | 40 | N/A | 1
3 | N/A | Team3 lacks techinical skills / knowledge to deliver the product within one semester | Personal schedule conflicts with project schedule (personal skill dependency), insufficient training time, team skill set may not cover the development of all the required functionality in the product | Individual make commitment to declare ownership on certain tasks, map out the full functionality and revisit team skill set coverage | 5 | 7 | 35 | N/A | 1
4 | N/A | Data access (Can I get the data to find trends?) | API capability / availability | Will investigate Facebook API for prototype | 3 | 10 | 30 | N/A | 1
5 | N/A | Client may have difficulty on integrating and maintaining the system | Missing the skilled personel | Provide documentation, maintain transparency with the client, select COTS that the client side staff are familiar with | 2 | 4 | 8 | N/A | 1
6 | N/A | Insufficient funds to provide functionality | Depend on the complexity of the system, we may need an actual budget to rent AWS etc | Client will provide funding once the needs are determined | 1 | 2 | 2 | N/A | 1

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Delayed win-win negotiation meeting | Pushed back the meeting to the following week
2 | Unbounded and vague project proposal | Moved forward based on assumptions
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | N/A | N/A
2
3
4
5