## SLOC
Team Number: | 3
Week: | 7
Program Size (SLOC) | Actual | Notes
Base
Added | 0 | Slow week due to delayed client meeting
Deleted | 0 | Slow week due to delayed client meeting
Modified | 0 | Slow week due to delayed client meeting
Reused | 2615 | Team Site
From COTS | 1802
Total New SLOC | 4417

## COTS
List of third-party components being considered for use in the system as of 10/31/2018
Component name | Functions of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black box | White box | Modify code
Flask | Python web framework | N/A | Backend server | Y
JSON web token | Authentication service standard | N/A | Backend server | Y
React | Javascript library | N/A | Frontend system |  | Y
Webpack | Javascript module bundler | N/A | Frontend system | Y
AWS | Cloud web service used for production | N/A | Backend system | Y
Heroku | Cloud web service used for prototyping | N/A | Backend system | Y
Swagger UI | API documentation and testing | N/A | Backend documentation |  |  | Y
Node JS | JS runtime environment | N/A | Frontend building environment | Y
Creative TIM | Component library | N/A | Style web app |  |  | Y
Material | CSS framework | N/A | Style web app | Y
mLab | database hosting service | N/A | Backend system | Y
MongoDB | Database | N/A | Store content ideas / user account info / team performance info etc | Y
Components that were filtered in the previous week
Component name | Rationale for filtering the component |  | Notes and References
none

## Progress
Progess Description
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. List your top priority works that must be accomplished in this week
1 | Prepare for project presentation on 11/2
2 | Update program model based on client feedback from ARB
3 | Update use cases based on client feedback from ARB prototype
4 | Conduct code review with Crucible
5 | Develop frontend UI further
6 | Develop backend API further and investigate AWS hosting
B. List dependencies or things/decision that you waiting for in this week
1 | Waiting on client to purchase a front end component library for the team
2 | Waiting to meet with client developer for feedback on technical design and maintainabiity
C. List your accomplishments from the previous week
1 | Developed ARB presentation documents and deliverables
2 | Compiled DC documentation package
3 | Updated project plan and life cycle plan for the idea management system based on client feedback post ARB
4 | Made improvements to idea endpoints on the backend API
5 | Conducted client meeting with System1 content manager
6 | Improved frontend UI for idea management system
7