## Risk
Top Project Risks as 10/31/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed | No. of Weeks Active
This Week | Last Week
1 | 1 | The product developed may not meet client's needs | Potentially unbounded scope; vague project description; short on time | More discussion with the client, conduct usability testing to gain enduser feedback on product design | 8 | 6 | 48 | Long turnaround time from the client. The scope has been narrowed down but changed again after the client meeting. Considering the point of time we stand in the semester, we may have insufficient time for development | 7
2 | 2 | Potential high learning curve for maintainers | Majority of the team do not plan to take CS577B. Need to have smooth handoff | Provide documentation to ensure smooth knowledge transfer | 5 | 4 | 20 | Decided to use React for frontend development and later found out that maintainers do not have React experience | 7
3 | 3 | Concurrency Issue | Multiple users upvote or edit at the same time | Handle each request one at a time | 4 | 3 | 12 |  | 2

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | HW3 transaction diagram and object analysis diagram | More thorough team review
2
3
4
5
6
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Had to redo win conditions, use cases, business flow etc due to pivot, which slowed down the development | Be transparent with all stakeholders as much as possible
2 | Had to update win conditions, use cases, business flow etc after client meeting on 10/31 which slowed down the development | Meet with stakeholders as frequently as possible to ensure the project is heading in the right direction at each iteration
3
4
5
6
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Delayed feedback from the client on ARB presentation and prototypes | Conducted client meeting on 10/31
2 | Delayed feedback from the client side developer on tech used in the system | Ping the client representative and wait for the client side developer feedback
3
4
5
6