## Risk
Top Project Risks as 10/03/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed | No. of Weeks Active
This Week | Last Week
1 | 2 | The product developed may not meet client's needs | Potentially unbounded scope, vague project description | More discussion with the client, conduct usability testing to gain enduser feedback on product design | 5 | 10 | 50 | Client has expressed interest in a different direction. Lack of direct contact with the end users | 4
2 | 4 | Access to historical data | API capability / dataset availability | Will further investigate data sources | 4 | 10 | 40 | Client has defined new needs with respect to trend identification requiring new data sources and historical dataset | 4
3 | 3 | Team3 may lack techinical skills to keep up with client's needs | Personal schedule conflicts with project schedule (personal skill dependency), insufficient training time, team skill set may not cover the development of all the required functionality in the product | Individual make commitment to declare ownership on certain tasks, map out the full functionality and revisit team skill set coverage, learn necessary skills along the way | 3 | 8 | 24 | No change | 4
4 | N/A | Database hosting may be difficult and costly | Resources required to scale database may become costly | Further investigate the scope of the data sources | 3 | 5 | 15 | New risk | 1
5 | 5 | Client may have difficulty integrating and maintaining the system | No direct contact with maintainers from the client side | Provide documentation, maintain transparency with the client, select COTS that the client side staff are familiar with | 2 | 5 | 10 | No change | 4
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Team members could have been more careful with Jira tickets | Conduct more standarized practice on Jira ticket management. I&IV person will review the tickets and notify the asignee to react before the deadline
2 | We could have been more careful with github commit message and Jira ticket ID | Be MORE CAREFUL when writing commit message
3
4
5
6
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Lack of client interaction before the presentation | Set a weekly or bi-weekly meeting time with client
2 | Facebook declined developer account | Get API key from client or resubmit FB approval request
3 | Use cases changed | Modify exising design to adapt to the changes
4
5
6
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Uncertainty in Twitter API developer account approval | Try to gain historical datasets from third sources to start investigating trends while awaiting approval
2
3
4
5
6