## SLOC
Team Number: | 3
Week: | 9
Program Size (SLOC) | Actual | Notes
Base
Added | 505 | backend:205 frontend: 300
Deleted | 56
Modified | 93
Reused | 2615 | backend, frontend, teamsite
From COTS | 2502
Total New SLOC | 5771

## COTS
List of third-party components being considered for use in the system as of 11/14/2018
Component name | Functions of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black box | White box | Modify code
Flask | Python web framework | N/A | Backend server | Y
JSON web token | Authentication service standard | N/A | Backend server | Y
React | Javascript library | N/A | Frontend system |  | Y
Webpack | Javascript module bundler | N/A | Frontend system | Y
AWS | Cloud web service used for production | N/A | Backend system | Y
Heroku | Cloud web service used for prototyping | N/A | Backend system | Y
Swagger UI | API documentation and testing | N/A | Backend documentation |  |  | Y
Node JS | JS runtime environment | N/A | Frontend building environment | Y
Creative TIM | Component library | N/A | Style web app |  |  | Y
Material | CSS framework | N/A | Style web app | Y
mLab | database hosting service | N/A | Backend system | Y
MongoDB | Database | N/A | Store content ideas / user account info / team performance info etc | Y
Components that were filtered in the previous week
Component name | Rationale for filtering the component |  | Notes and References
none

## Progress
Progress Description
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. List your top priority works that must be accomplished in this week
1 | Prepare for CCD presentation
2 | Implement logout flow/token refresh
3 | Protect routes according to access privileges for new user roles
4 | Refactor PUT route for ideas endpoint
5 | Debug Heroku deployment
6 | Deploy app to AWS
7 | Refactor config file for production
8 | Document API via swagger fields
9 | Export publishing calendar to CSV file
10 | Update UI
11 | Integrate with backend API
12 | Test auth endpoints
13 | Test users endpoints
14 | Test ideas endpoints
15 | Test goals endpoints
16 | Test utilities
17 | Update FED
18 | Update LCP
19 | Update TPC
20 | Update SSAD
21 | Update OCD
22 | Implement User manual
23
24
B. List dependencies or things/decision that you waiting for in this week
1 | Waiting to meet with client developer for feedback on technical design and maintainability
2
C. List your accomplishments from the previous week
1 | Made improvements to idea endpoints on the backend API
2 | Improved frontend UI for idea management system
3 | Prepare for project presentation on 11/2
4 | Update program model based on client feedback from ARB
5 | Update use cases based on client feedback from ARB prototype
6 | Conduct code review with Crucible
7 | Update Diagrams
8 | Refactor user model to account for new user role types
9 | Refactor auth decorators to account for new user role types
10 | Create goal model
11 | Create GET/POST routes for goal list
12 | Create GET/POST/PUT/DELETE routes for goals route