## Risk
Top Project Risks as 11/14/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed | No. of Weeks Active
This Week | Last Week
1 | 1 | The product developed may not meet client's needs | short on time, core capability are not met or unfinished product, poor communication with the client | More discussion with the client & maintainer, conduct usability testing to gain enduser feedback on product design, integrate frontend and backend in a timely manner | 8 | 5 | 40 | Long turnaround time from the client. The scope has been narrowed down but changed again after the client meeting. Considering the point of time we stand in the semester, we may have insufficient time for development. CCD is postponed to the following week. | 9
2 | 4 | Concurrency Issue | Multiple users edit at the same time | Handle each request one at a time | 4 | 4 | 16 | Proposed fallback MVP by negotiating with the client about implementation decisions: limiting user priviledge on editing pitches | 4
3 | 2 | Potential high learning curve for maintainers | Majority of the team do not plan to take CS577B. Need to have smooth handoff | Provide documentation to ensure smooth knowledge transfer | 3 | 4 | 12 | Decided to use React for frontend development and later found out that maintainers do not have React experience | 9

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Project presentation narrative could have been slower and with more details | Incorporate feedback in future presentation, rehearsal more
2 | Project presentation slide deck could have been less verbose | Incorporate feedback in future presentation, trim slide deck, focus on important information, put extra information in appendix
3
4
5
6
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Had to redo win conditions, use cases, business flow etc due to pivot, which slowed down the development | Be transparent with all stakeholders as much as possible
2 | Had to update win conditions, use cases, business flow etc after client meeting on 10/31 which slowed down the development | Meet with stakeholders as frequently as possible to ensure the project is heading in the right direction at each iteration
3 | Frontend UI developer on Travel in Tokyo for a week and half | focus on crucial tasks with respect to frontend implementation, delegate tasks to others team members (Should have brought the team with him)
4 | CCD was postponed | Update project plan to reflect the new schedule
5
6
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Delayed feedback from the client side developer on tech used in the system | Ping the client representative again and wait for the client side developer feedback
2
3
4
5