## Technical Debt
Technical Debt
Describe technical debt of your project :
| 1. Please describe your technical debt in Description | 4. Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5. If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7. Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitgation plan | No. of weeks active
1 | Hierarchy level limited by DB design: rushed database design due to ARB timeline after pivot | Life Cycle Management Shortfalls | Reckless deliberate | Yes | Discussed DB design further as a team and refactored database models based on discussion | 5
2 | Limited automated testing -- need to implement more tests | Life Cycle Management Shortfalls | Reckless deliberate | No | Test existing features and write tests in parallel to new development efforts moving forward | 7
3 | Some API endpoints are getting large and logically complex | Life Cycle Management Shortfalls | Reckless deliberate | Yes | Refactored backend into separate routes encapsulating smaller chunks of logic | 2
4 | Not all code is commented and documentation is incomplete | Life Cycle Management Shortfalls | Reckless deliberate | No | Conduct code review then implement documentation | 7
5 | Delayed integration between frontend and backend due to time pressure | Methods tools and process shortfalls | Reckless deliberate | No | Start integration as soon as possible | 2

## Category1_Example
Description | Examples
Life Cycle Management Shortfalls: | •Debt resulted from schedule pressure due to scope creep where additional features are added without altering the project scope and schedule.
This includes any debt resulted from the software life cycle management shortfalls such: budgeting, requirements, contracts, scheduling, etc. | •Debt resulted from a third-party-estimate where a technical lead make an ignorant- estimation on how long it will take and cost to developed and the actual team are held responsible for these estimation.
•This might include not preforming an automated testing due to schedule pressure, having duplicated code since there is no time to refactor,etc.
Personal Shortfalls:
This includes any debt resulted from people shortfalls | •Debt resulted from the project team such as adding or removing a team member.
such as: not having enough experience, change in team composition,etc. | •Debt resulted from the project team skills such as not having enough experience with the development language.
•This might include: Delaying unit testing until the new tester join the team, not preforming unit testing due to lack of experience.
Methods, tools, and process Shortfalls:
This include any debt resulted from Methods, tools, and process Shortfalls: such as tools limitations, process nature, etc. | •Debt resulted from tool limitation such as the inability to integrate with the API.
• Debt resulted from the process such as : not testing the code until the last minute since we are using waterfall
•This might include: delaying testing due to the process, delaying integration, not following the architecture specification due to language limitations

## Technical Debt Example
Technical Debt
Each team should submit two copies: One will be completed by the Quality Focal Point and the other one will be completed by the team.
Describe technical debt of your project :
| 1.Please describe your technical debt in Description | 4.Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5.If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7.Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitigation plan | No. of weeks active
1 | Due to time constraint, we will stop working on the French language option for this release even though the company will open a store in France in 3 years. | Life Cycle Management Shortfalls | Prudent_Deliberate | No | We are working on the English version, and will provide the client with a detailed technical explanation on how to support other languages | 10
2
3
4
5
6
7
8
9
10