## Risk
Top Project Risks as 10/17/2018
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed | No. of Weeks Active
This Week | Last Week
1 | 1 | The product developed may not meet client's needs | Potentially unbounded scope, vague project description | More discussion with the client, conduct usability testing to gain enduser feedback on product design | 8 | 5 | 40 | Client has expressed interest in a different direction. Lack of direct contact with the end users | 5
2 | 5 | Potential high learning curve for maintainers | Majority of the team do not plan to take CS577B. Need to have smooth handoff | Provide documentation to ensure smooth knowledge transfer | 5 | 4 | 20 | Decided to use React for frontend development and later found out that maintainers do not have React experience | 5
3 | N/A | Concurrency Issue | Multiple users upvote or edit at the same time | Handle each request one at a time | 4 | 3 | 12 | New risk | 0

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Team members could have been more careful with Jira tickets | Conduct more standarized practice on Jira ticket management. I&IV person will review the tickets and notify the asignee to react before the deadline
2 | We could have been more careful with github commit message and Jira ticket ID | Be MORE CAREFUL when writing commit message
3
4
5
6
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Jira was down before the deadline | More reliable server for Jira, potentially have earlier meetings
2 | Had to redo win conditions, use cases, business flow etc due to pivot, which slowed down the development | Be transparent with all stakeholders as much as possible
3
4
5
6
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Schedule is tight for ARB Presentation due to late re-pivot | Team will invest more time to make sure all deadlines are met
2
3
4
5
6