## SLOC
Team Number: | 5
Week: | 5
Program Size (SLOC) | Actual | Notes
Base
Added | 2403 | backend: 603 frontend: 1800
Deleted | 0 | New development due to pivot
Modified | 0 | New development due to pivot
Reused | 212 | Team Site
From COTS | 2615
Total New SLOC

## COTS
List of third-party components being considered for use in the system as of 10/17/2018
Component name | Functions of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black box | White box | Modify code
Flask | Python web framework | N/A | Backend server | Y
JSON web token | Authentication service standard | N/A | Backend server | Y
React | Javascript library | N/A | Frontend system |  | Y
Webpack | Javascript module bundler | N/A | Frontend system | Y
AWS | Cloud web service used for production | N/A | Backend system | Y
Heroku | Cloud web service used for prototyping | N/A | Backend system | Y
Swagger UI | API documentation and testing | N/A | Backend documentation |  |  | Y
Node JS | JS runtime environment | N/A | Frontend building environment | Y
Creative TIM | Component library | N/A | Style web app |  |  | Y
Material | CSS framework | N/A | Style web app | Y
mLab | databse hosting service | N/A | Backend system | Y
MongoDB | Database | N/A | Store content ideas / user account info / team performance info etc | Y
Components that were filtered in the previous week
Component name | Rationale for filtering the component |  | Notes and References
Twitter API | Data source access |  | No longer in scope
Facebook API | Data source access |  | No longer in scope
Feedparser | Python library |  | No longer in scope
SharedCount API | Competative analysis |  | No longer in scope
Yahoo API | WOEID lookup |  | No longer in scope
adBeat API | Competative analysis |  | No longer in scope
scrapy | Python web crawler framework |  | No longer in scope

## Progress
Progess Description
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. List your top priority works that must be accomplished in this week
1 | Implement DC package
2 | Prepare for project presentation on 11/2
3 | Continue to develop frontend UI
4 | Continue to develop backend system
B. List dependencies or things/decision that you waiting for in this week
1 | Stakeholder meeting with client involved
2 | Waiting for stakeholder feedback based on ARB prototype demo
C. List your accomplishments from the previous week
1 | Updated use cases for client's proposal of idea management system
2 | Updated program model for the new idea management system
3 | Implemented backend user and idea endpoints for idea management API prototype
4 | Implemented frontend UI prototype for idea management system
5 | Implemented ARB presentation slide deck
6 | Updated project plan and life cycle plan for the new idea management system